## Sayfa1
October
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Planning | bar: October 1 to October 5
2 | Detail design of project | bar: October 4 to October 9
3 | Research on Project related technologies | bar: October 4 to October 9
4 | Requirement Analysis | bar: October 5 to October 10
5 | Content writing and assembly | bar: October 6 to October 10
6 | Design of interface | bar: October 8 to October 9
7 | Coding | bar: October 8 to October 21
8 | Testing and Evaluation | bar: October 15 to October 22
9 | Midpoint Review | bar: October 9
10 | Midpoint Review (Final) | bar: October 23
11 | Documentation | bar: October 19 to October 23